## Sheet1
DABI Project Gantt chart
Days remaining | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
 | time axis 2024-01-29 to 2024-03-25
 | time axis 2024-01-29 to 2024-03-25
Key dates | 2024-02-19: 1; 2024-03-10: 2; 2024-03-25: 3
General tasks
Set up github accounts | bar: 2024-01-29 to 2024-02-06
Review week 6 material | bar: 2024-01-29 to 2024-02-06
Data Wrangling
Load json files and put files into dataframes | bar: 2024-01-29 to 2024-01-31
Deal with missing values
Create binary variables for categories
Combine data into one dataframe
EDA
Look at cutomer demographics
Clustering
Research clustering methods
Decide on clustering algorithm
Report
1st draft
Final draft
Key dates
1. Peer assessment submission 19th February
2. Peer assessment feedback 10th March
3. Project submission 25th March
Project questions (from project sheet)
1. Identify clusters of customer that completed more transactions and/or spent more money over the promotional period.
2. Provide an interpretation of clusters with visual representations of each cluster.
3. Provide a clear description of customer characteristics that the company should focus their attention to and explain why.